## Slide 1: Older Adult Transportation Initiative
Nov 10, 2021
Agenda:
Updates on transportation pilots underway
Learnings/discussion
Update on ARPA proposal for off-island medical transportation pilot
Review of our priorities/plan for 2022 (and where you can lean in)

## Slide 2: Where are we today – Pilot Review
 | Taxi Program at IEH | GoGoGrandparents | Anchors Transportation Pilot | Center4Living
Purpose | Essential - Medical appointments only (scheduled) | Essential and Enrichment (on demand/scheduled) | To provide alternative multi-rider transportation solution in Edgartown (scheduled) | To provide client transportation to C4L (scheduled)
Program description | IEH schedules taxi rides for clients | Referral program from service agencies – HAMV registers and oversees | Provides fixed loop in Edgartown (post office, pharmacy, grocery store) initially; may add transportation to programs at the Anchors | Picks up and delivers clients to the center/home, potential expansion to other uses
Partner | Local taxi operator with fixed pricing, 100% costs covered | GoGoGrandparent (concierge service) 100% costs covered | VTA provides vehicle, insurance, driver training; Anchors provides staff driver and volunteer drivers | VTA provides vehicle, C4L provides driver

## Slide 3: Note: Anchors Solution reflects our initial vision for scheduled on island transportation (Bus Plus ++)
2+ electric/hybrid vehicles*
Single** use for those with impairments & van for 6-8 riders
Hybrid model
2 paid FTEs, dispatcher/coordinator and 1 driver and volunteer drivers
Storage and maintenance of vehicles by 3rd party organization (VTA, church etc.)
Phone to register/request ride 24 hours – 1 week in advance
Scheduled circular route on-island (e.g. up-island early morning etc.) with door-to-door service, multiple riders
Vehicles do not require CDL licensing; **vehicle options for those impaired can be either single or multiple riders)

## Slide 4: Note: C4L approach reflects one of our initial options – Get me to the “program” on time!
2+ electric/hybrid vehicles*
Single** use for those with impairments & van for 6-8 riders
Hybrid model
2 paid FTEs, dispatcher/coordinator and 1 driver and volunteer drivers
Storage and maintenance of vehicles by 3rd party organization (VTA, church etc.)
Organization makes ongoing reservations (daily, weekly etc.) for clients attending their programs
Round trip door to door pick-up for Older Adult program attendees-single point drop off**
** Possible Point-to-point delivery of goods when van is not in use or could be used for “companionship travel”

## Slide 5: Where are we today – Pilot Review
 | Taxi Program at IEH | GoGoGrandparents | Anchors Transportation Pilot | Center4Living
Number of trips to date | 100 (approximate) to 1 location (MVH) | 95 trips to location of client’s choice | N/A | 
Cost per mile (average) | $3.50 (single rider) – including tip | $6.02: range is $3.50 - $22.19 (single rider): shorter rides with congestion cost the most | $1.00- $2.00 (estimated); up to 4 riders | 
Cost per trip (average) | $12.50 -$13.50 | $29.01 (average rides to be 4.8 miles)* | TBD | 
Plans | Continue thru the winter (will not run Blueberry Van) | Pilot to continue at least thru end of the year (ideally thru winter) | Up and running TBD | Running now; seeking financial support for paid driver
For apples-to-apples comparison, Tisbury to MVH via GoGo ranges from $17 -19.00

## Slide 6: GoGoGrandparent Update - Stats Updated
Attribute | 7/27 to 9/15 | 7/27 to 11/7
Number of participants | 6 | 14
Number of rides | 26 | 95
Average Cost per ride | $22.91 | $29.40
Min/Max cost per ride | $11.66-$67.76 | $11.66- $67.76
Total number of miles | 82.3 miles | 463 miles
Average ride distance | 3.2 miles | 4.88 miles
Min/Max number of miles | .7 mile - 10 miles | .7 mile- 12 miles
Min/Max ride time | 7 minutes-40.7 minutes | 7 minutes – 40.7 minutes

## Slide 7: What our participants have to say
Likes
Drivers courteous and respectful
Appreciative of costs being covered
Dislikes
Can’t schedule multiple stops (w/o driver’s agreement) for daily errands
Long wait times for an operator/finding ride
In their own words
“feels like they aren’t ready for prime-time yet”
“Love it- just what the island needs”
Lack of relevant recorded messages to Island participants while waiting for an operator
A viable solution to public transportation when that option can’t work
Flexibility to go beyond medical appointments a positive (although oftentimes the initial reason to use GoGoGrandparents)
“Seems to be working better in the off-season”
“Good to have this as an option”
“Won’t use it again because they won’t wait while I shop”
Some inconsistency in quality of Operators knowledge and communication skills

## Slide 8: Transportation Model Implications – Lessons Learned
Time is money – especially for the GoGoGrandparents model
  As congestion arises, costs rise as well
  Surges are more likely up-island and typically disappear by the time a driver is found
Older Adults desire multiple stops or a round trip (e.g. wait while they get a booster shot) on a single journey (post office, pharmacy etc.) but not always aligned with the GoGoGrandparents or taxi model
Preference for scheduled trips (versus on-demand) raises uncertainty regarding available drivers (or longer wait times for drivers)

## Slide 9: Transportation Model Implications – Lessons Learned (2)
Any solution that includes using an app is “dead in the water”
Longish wait times with Operators make it hard to get home w/o a usable cell phone when you have to schedule from the road
Referral model via service agencies for program enrollment/education is most effective way to raise awareness and usage; some may also wish to provide transportation services

## Slide 10: Our initial Building Blocks of On-Island Scheduled Solution still resonate with varying degrees of success
Solution Guardrails
7 days a week operation
Round trip guarantee (maximum of 30 minutes wait time for on-demand return trip)
Available 7 am – 10 pm
A minimum of 24 hours to schedule beforehand
No additional charge for caregivers
Drivers willing to wait
Single touch for rider (1 call to arrange) in English and Portuguese
Human interaction with knowledgeable person with a caring spirit
Individual or organization can schedule rides (single or multiple)
Online reservation solution option
Data tracking – performance and safety/security
No cash exchanged (done beforehand)
Comfortable riding experience
Door-to-door service
Available to those with impairments (physical, cognitive, hearing etc.)
Electric or hybrid vehicles
Red indicates issues
Blue – criteria under consideration to add

## Slide 11: GoGoGrandparent Pilot Reflections/Discussion
                Based on what we’ve learned to date;
                What do we keep doing?
                What do we stop?
                What do we do differently?
                How do we build on our learnings?

## Slide 12: GoGoGrandparent Pilot Next Steps
Expanding pilot program to 20+ participants – so get the word out!
Exploring ways we can partner differently with GoGoGrandparents (we are innovative, they are too)
Will continue pilot through November/December
Looking for additional sources of funding for pilot continuation through the winter
Pilot has been positioned for “on-demand” transportation, scheduling ahead option will be tested going forward
Should we consider for medical, off-island solution as well?

## Slide 13: ARPA Submission
Project Name: Older Adult Off-Island Medical Transportation Pilot Program
Amount Requested: $377,400 Total Project Cost: $661,320 (includes in-kind contribution from HAMV, volunteers, and Coalition members)
Project Goals: To provide daily, on-demand door-to-door transportation for off-island medical, vision and oral care appointments for any Older Adult (and a caregiver or ride-along volunteer) on a sliding fee scale.
Beginning and Ending Dates of the Project/Campaign: Nov, 2021 – Oct 2023 (2 years)

## Slide 14: Why ARPA?
Funder’s Priorities: This request directly addresses Category #1 - by supporting the public health response (as stated in the FACT SHEET, pages 3 & 4, “support for vulnerable populations to access medical or public health services” and “services or outreach to promote access to health and social services”).
It is well documented nationally that COVID impacted many Americans (of all ages) ability to receive ongoing medical and dental care, due to lack of available resources for routine care, fear of visiting medical or dental institutions due to perceived safety risks and, for some, lack of time (due to caring for family members), strained financial resources and lack of transportation (including anxiety of getting ferry reservations and the associated costs).

## Slide 15: Target Population for this solution
Older Adults 65+ (approximately 5,700) with a focus on Older Adults with incomes <$50k and those who do not qualify for Mass Health. Our data indicates that this income range represents approximately 30% of Older Adult households on the Island. Those with higher incomes can access this transportation option at a higher cost and help subsidize the cost for others.

## Slide 16: Curb-to-curb transportation for Older Adults (when other means are unavailable or unaffordable)
COAs are the initial contact for request (phone) from Older Adults
Hybrid model
1 paid project coordinator & volunteer drivers and support ride-along*
COA contacts project coordinator who works with the Steamship for ferry and VTA for round trip transport
VTA provides dispatch capability to notify volunteer drivers
Vehicles provided by the VTA and/or volunteer driver vehicles
*
Volunteer drivers and support ride-along could be sourced through Elder Services RSVP program;

## Slide 17: 2 year overview
Phase 1 Getting Started – Months 1-6
Phase 2 – Early Stage Pilot (Months 7-12)
Phase 3 – Full Scale Pilot (Months 13-24)

## Slide 18: Expected Outcomes
There are 4 measurable outcomes for this program;
A viable program model (do we have adequate volunteers, etc. to meet the need)
The number of Older Adults who participate in the program (pilot and scale)
Satisfaction with the program and impact on their lives (pre/post participation surveys)
Awareness of the program (annual survey)

## Slide 19: On our plate – how to keep the momentum going?
Moving forward with our key priority: Off-island Medical transportation
Continuing on with Pilot Program for GoGoGrandparents
Raising awareness/communicating current transportation options
    How can we support existing solutions/partnering with VTA and other options?
    Do we see this as a priority/important for creating change with Older Adults
Looking for partners
Looking for funding

## Slide 20: HAMV key priorities for an Aging Friendly Island
Ensure that the essential services Older Adults need and the workforce necessary to provide them are in place.
Expand Older Adult transportation options and raise awareness of these options.
Expand opportunities for community engagement (coordinated volunteer program, time banking, educational programs etc.).
Centralize critical information sources that are fit-for-purpose with demographic preferences in mind.
Support digital equity and inclusion for Older Adults focusing on ongoing education/assistance.
Address Older Adult safety/accessibility regarding infrastructure (roads, sidewalks, bike paths, beaches) to support their lifestyle aspirations.

## Slide 21: Key Initiative #2
Strategy | Action Steps | Partners | Year
Create an island-wide integrated vision/support for alternative transportation options for Older Adults (on island essential and enrichment) & off-island medical transport) | Convene a coalition of stakeholder organizations to: Address perceived service gaps Create options to encourage a transition from “driving myself” to utilizing alternative transportation modes Create shared-usage solutions for all partners serving Older Adults Minimize inefficiencies in a solution/reduce road congestion | Center for Living Edgartown COA Island Elderly Housing IGI MVCF (partner) MVCS MVC (partner) Oak Bluffs COA Tisbury COA Up-island COA Vineyard Villages at Home VTA Wampanoag Tribe of Gay Head YMCA | 2021
Goal: Expand Older Adult transportation options and raise awareness of these options.
Board advocate: Lyndsay Famariss/Cindy Trish
WHO Domain: Transportation

## Slide 22: Key Initiative #2
Strategy | Action Steps | Partners | Year
(cont.) | Review Older Adult survey data to understand transportation behaviors and needs | S/A | 2021
 | Conduct an audit of transportation options on and off-island | S/A | 2021
 | Explore what other communities are doing to address Older Adult transportation needs | S/A | 2021
 | Identify priorities for solution building for on and off-island transportation options | S/A | 2021
Goal: Expand Older Adult transportation options and raise awareness of these options.
Board advocate: Lyndsay Famariss/Cindy Trish
WHO Domain: Transportation

## Slide 23: Key Initiative #2
Strategy | Action Steps | Partners | Year
(cont.) | Create transportation solutions options for target audience for on and off-island | S/A | 2021
 | Secure funding for Pilot program for on-island transportation solution (GoGoGrandparents) | S/A | 2021
 | Evaluate effectiveness of on-island pilot program and secure funding for longer term program | S/A | 2022
 | Identify Pilot program for-off-island medical transport and secure funding | S/A & Dylan Fernandes | 2022
Goal: Expand Older Adult transportation options and raise awareness of these options.
Board advocate: Lyndsay Famariss/Cindy Trish
WHO Domain: Transportation

## Slide 24: Key Initiative #2
Strategy | Action Steps | Partners | Year
(cont.) | Evaluate effectiveness of off[-island medical transport pilot program and secure funding for longer term program | TBD, Dylan Fernandes | 2023
Raise awareness of existing transportation options for Older Adults | Identify optimal ways to share information (digital, hardcopy, phone program) | S/A | Q1, 2022
 | Create a communications campaign to raise awareness of existing options | VTA, town governments, S/A | Q2, 2022
 | Roll-out awareness/education program | S/A | Q3, 2022
Goal: Expand Older Adult transportation options and raise awareness of these options.
Board advocate: Lyndsay Famariss/Cindy Trish
WHO Domain: Transportation

## Slide 25: Looking for participation 2022
Off-Island Medical Transportation
GoGoGrandparents
Communications Campaign for available transportation options
Cindy will follow up with each of you individually to hear your feedback on our efforts this year and how you would like to participate.
2022 Calendar
  Monthly meetings Jan – June
  Summer Hiatus
  Monthly meetings Sept - Dec